## Sales Baba
|  |  |  | HIGH | MED | LOW | TOTAL
| PROJECT NAME |  | CLOSED
| Seraikela |  | INPROGRESS
| DATE |  | OPEN
21/01/2020
SNO | SCREEN NAME (DC Login) | ISSUE DESCRIPTION | PRIORITY | RAISED BY | STATUS | OPENED ON | CLOSED ON | COMMENTS
1 | Settings->User | Every time Mr. Title is shown by default instead of any other title being selected
2 | Settings->Geo Structure | Structure spelling error in geo structure module
3 | Settings->Geo Structure | Every where there is organization which should be removed because by default it is Seraikela
4 | Settings->Geo Structure | Inactive members are also coming in officer's drop down menu
5 | Settings->Geo Structure | No star mark in district, subdivision, block but the fields are mandatory
6 | Settings->Geo Structure | While adding if we click on reset button the validation messages are not being removed
7 | Settings->Geo Structure | Village spelling error in add form
8 | Settings->Department | After making the department inactive it is still shown in dashboard
9 | Settings->Department | While adding if we click on reset button the validation messages are not being removed
10 | Settings->Year | While adding if we click on reset button the validation messages are not being removed
11 | Settings->Designation | While adding if we click on reset button the validation messages are not being removed
12 | Settings->Scheme Types | While adding if we click on reset button the validation messages are not being removed
13 | Settings->Scheme Types | While editing the message also the alert box says scheme added successfully
14 | Layout->Side bar | Category and sub category spelling error
15 | Settings->Resource Category | Category spelling error on the title of the screen
16 | Settings->Resource Category | While editing the message also the alert box says scheme added successfully
17 | Settings->Resource Category | In validation the resource category name shows error
18 | Settings->Resource Sub Category | Desciption should not be mandatory
19 | Settings->Resource Sub Category | While editing the message also the alert box says scheme added successfully
20 | Settings->UoM Type | While editing the message also the alert box says scheme added successfully
21 | Layout->Side bar | UOM should be UoM
22 | Settings->UOM | In every alert box and the title plus the the table should have spelling as UoM which is currently UOM
23 | Resourcers->Define Resources | Sub Catagory spelling error in add of resources
24 | Resourcers->Define Resources | While editing resource also the alert dialog box pops as new resource has been added
25 | Resourcers->Define Resources | Validation missing in Sub Resourcee
26 | Resourcers->Define Resources | During add resources the inactive department are also prersent in the drop down menu
27 | Schemes->Define Schemes | Inactive departments are also coming in department section while adding schemes in the drop down menu
28 | Schemes->Define Schemes | Select Asset is (*) marked and no validation is done
29 | Schemes->Define Schemes | Attribute section while adding attribute there is no validation, only required field is being used
| Schemes->Scheme Performance | While adding coordinates, we need to get validation